Project Charter Template

(Office/Department - Project Name)

Updated (date) - Version (x.x)

| Project Name |  |  | UW-Madison Office Move |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Executive Sponsor |  |  | UW-Madison Department Chair |  |  |  |
| Project Manager |  |  | Dylan Smith |  |  |  |
| Primary Stakeholder(s) |  |  | UW-Madison CFO, UW-Madison Department Chair |  |  |  |
| Project Description / Statement of Work |  |  |  |  |  |  |
| The purpose of this project is to manage an important campus move that includes the coordination of an office remodeling project and moving staff from two office units into a consolidated space |  |  |  |  |  |  |
| Business Case / Statement of Need (Why is this project important and why is it important now?) |  |  |  |  |  |  |
| UW-Madison has been awarded a $5 million grant for an innovation research project that is scheduled to begin in 6 months. The office space needs to be ready for occupancy in 5 months to allow the move to occur during month 6 so everyone is in place for the official kickoff of the $5 million innovation grant. The 78 people are currently located in two different buildings on campus. |  |  |  |  |  |  |
| Customers (Direct users/Those impacted by the project) |  |  |  | Customer Needs / Requirements |  |  |
| UW-Madison Department Heads |  |  |  | Maximize flexibility and mobility of the space |  |  |
| UW-Madison Team Leads |  |  |  | Usable office space, wireless connections, portable cubicle walls |  |  |
| Project Definition |  |  |  |  |  |  |
| Project Goals | Move the 78 people currently located in two different buildings into one space within six months. |  |  |  |  |  |
| Project Scope | The scope of the project includes overseeing the schedules for demolition as well as coordinating the ordering of new furniture/ computers, and the construction. It also includes coordinating the move of the staff into their new space. |  |  |  |  |  |
| Project Deliverables | Demolition schedule, plan for ordering the furniture, plan for wiring electrical and internet, space layout and design |  |  |  |  |  |
| Project Risks (Actions, events, and situations outside the project plan that may positively or negatively impact the project) |  |  |  |  |  |  |
| The space layout and design fails inspection, the furniture does not arrive on time, the demolition goes long, there are delays in construction |  |  |  |  |  |  |
| Implementation Plan / Milestones) (Due dates and durations) |  |  |  |  |  |  |
| Month 1 – Design proposal approved, Construction contract awarded Month 2 – Order modular furniture Month 3 – Begin demolition Month 4 – Begin construction Month 5 – Modular office installation Month 6 – Complete the move |  |  |  |  |  |  |
| Project Budget / Resources (Money, people, services, materials, etc.) |  |  |  |  |  |  |
| $450,000 |  |  |  |  |  |  |
| Communication Plan (What needs to be communicated? When is communication needed? To who? How?) |  |  |  |  |  |  |
| 30 minute weekly updates with key stakeholders, 15 minute standups with construction crew |  |  |  |  |  |  |
| Change Management / Issue Management (How decisions will be made? How changes will be made?) |  |  |  |  |  |  |
| An issue spreadsheet will be created and reviewed with project stakeholder during weekly meetings |  |  |  |  |  |  |
| Project Team Roles and Responsibilities |  |  |  |  |  |  |
| Team members |  | Roles |  |  | Responsibilities |  |
| Construction Foreman |  | Construction Foreman |  |  | Manages the construction |  |
| Interior Designer |  | Interior Designer |  |  | Designs the layout and selects the modular furniture |  |
| Stakeholder Roles and Responsibilities |  |  |  |  |  |  |
| Stakeholders |  | Roles and Responsibilities |  |  |  |  |
| UW-Madison Department Heads |  | Review issues and approve plans |  |  |  |  |

Sponsor Sign-off

Date:

(Name, Role)