## Project Planner
MetroMobility Data Analytics Project Schedule
Projected Start Date: Monday, January 5, 2026 | Projected End Date: Wednesday, September 23, 2026 |  |  |  | Total duration: 180 business days |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
MILESTONE | PLANNED START DAY | PLAN DURATION (DAYS) | ACTUAL START | ACTUAL DURATION | TEAM MEMBERS RESPONSIBLE | RESOURCES REQUIRED | PERCENT COMPLETE | PERIODS
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180
Project charter review and approval | 1 | 1 |  |  | Project Manager | Project charter draft, documentation tools | 0%
Project management plan development | 1 | 7 |  |  | Project Manager | Project budget draft, stakeholder register | 0%
Define data privacy requirements | 1 | 2 |  |  | Data Analytics Team Lead | Legal data privacy guidelines | 0%
Identify existing moblity data sources | 3 | 28 |  |  | Data Analytics Team | Access to vendor and agency datasets | 0%
Assess data availability and quality | 3 | 7 |  |  | Data Analytics Team Lead | Sample datasets from each source, data profiling tools | 0%
Identify performance metrics | 31 | 7 |  |  | Project Manager, Data Analytics Team Lead | Workshops with city planners and data analytics team | 0%
Define KPI calculation methodologies | 38 | 3 |  |  | Data Analytics Team | KPI formula templates | 0%
Standardize KPIs across agencies | 41 | 14 |  |  | Data Analytics Team | KPI documentation, cross-agency meetings | 0%
Validate KPIs with stakeholders | 55 | 5 |  |  | Project Manager, Data Analytics Team Lead | Stakeholder review meetings | 0%
Finalize approved KPI list | 60 | 3 |  |  | Data Analytics Team Lead | KPI drafts | 0%
Define overall system architecture | 63 | 7 |  |  | Data Architect, Data Analytics Team Lead | Architecture diagrams, modeling tools | 0%
Select data warehouse approach | 70 | 5 |  |  | Project Manager, Data Architect | Vendor whitepapers, cost estimates | 0%
Define data integration processes | 75 | 7 |  |  | Data Engineers, Data Architect | ETL design tools | 0%
Define data security & privacy measures | 82 | 5 |  |  | Security Analyst, Project Manager | Compliance guidelines, legal input | 0%
Evaluate technology platforms & tools | 87 | 3 |  |  | Project Manager, Data Architect | Vendor demos, trial licenses | 0%
Develop system architecture documentation | 90 | 10 |  |  | Data Architect | Documentation tools | 0%
Set up pilot data warehouse environment | 100 | 10 |  |  | Data Engineers | Cloud infrastructure, DB software | 0%
Develop data tables and models | 110 | 10 |  |  | Data Engineers | Data modeling tools | 0%
Build ETL pipelines | 120 | 15 |  |  | Data Engineers | ETL framework, APIs | 0%
Implement data privacy controls | 135 | 5 |  |  | Security Analyst, Data Engineers | Encryption tools | 0%
Validate and test integrated data environment | 140 | 7 |  |  | QA Analyst, Data Analytics Team | Test datasets, validation scripts | 0%
Resolve data quality issues | 147 | 8 |  |  | Data Engineers | Data profiling tools | 0%
Define dashboard requirements | 155 | 5 |  |  | Project Manager, Stakeholders | Requirements workshops | 0%
Design dashboard user interface | 160 | 7 |  |  | UX Designer, Data Analytics Team | UI wireframing tools | 0%
Develop dashboards and connect to warehouse | 167 | 8 |  |  | Data Engineers | Dashboard UI software, DB software | 0%
Dashboard testing & stakeholder review | 175 | 3 |  |  | QA Analyst, Stakeholders | UAT sessions | 0%
Final reporting, policy recommendations, closeout | 178 | 3 |  |  | Project Manager, Data Analytics Team Lead | Final reports, presentation decks | 0%